# Artemis Training

Project Plan

Contents

Revision Table	3

Overview	4

Scope	4

Assumptions and Constraints	4

The Project Statement of Purpose	5

Front End Analysis	5

Performance Improvement Analysis	5

Gaps that can be closed through training	5

Gaps that cannot be closed through training:	5

Training Needs/Gap Analysis	5

Desired performance	5

Actual Performance	5

Performance gap = desired –measured	5

Job Analysis	5

Specific duty areas	5

Task analysis	6

Learning Objectives	6

Target Audience	6

Users	6

Task Descriptions	6

Ads	6

FMBM	6

Article	7

Issue	7

Training Class Timelines	8

Usability Goals (Requirements)	9

Existing Documentation	9

Product Design Implications	9

Document Specifications	10

Instructional Design	10

Platforms Supported	10

Graphics and Media	10

Delivery	10

Extras	10

Process, Estimates, and Schedule	11

Milestones	11

Reviews and Approvals.	12

Resources	13

Documentation Team	13

Other Teams	13

Hardware, Software, Tools	13

Assets	13

Potential Risks and Issues	13

# Revision Table

| Changes | Date | Revision Number |
| --- | --- | --- |
| Initial document creation | 12/04/2014 | 0.1 |
| Changes from Susan Clark addressed/incorporated | 12/05/2014 | 0.2 |

# Overview

This document is provided to DJS staff interested and involved in the Artemis project, with a specific interest in the user training. This document describes the project plan for developing the user training for the Artemis web application. It will give you an overview of the project, talk about the audience, describe the tasks, goals, and other issues needed to understand the project.

## Scope

The training will be an introduction to what Artemis is and what it is designed to replace. It will cover the tasks needed to work on Ads, FMBM, Articles, and Issues.

We won’t teach workflows. To take a workflow approach would require separate training for each workflow. That’s inefficient, and likely not really necessary. It is probably more important for learners to know what the different Artemis tasks are and how to perform them. They can then use their judgment and knowledge to apply these for their specific workflow. For example, knowing when and how to perform the Artemis (AR) FreeStyle Processing task is important; using it in in a specific workflow ican be discussed during the training class.

## Assumptions and Constraints

We’re making the following assumptions:

- Learners are familiar with their current production tasks, and ‘mapping’ them to Artemis won’t be difficult.

- The terminology is known as well.

Our constraints are:

- Resources.

  - Steve Arrants has additional tasks (ArticleExpress: Help, videos; Artemis: Help, videos; ePAGE: Help)

  - Susan Clark is currently 50% on training. In addition we anticipate that she may be the first line support—previously trained users may ask her questions during Artemis use.

- Time. There are some industry estimates that Instructor Led Training (ILT) takes the following ratios of time to develop/amount of training:

  - 22:1 ILT training of simple learning content, repurposing existing material, minimal learning support materials (job aids).

  - 43:1 - ILT training, average project for creating corporate ILT class with well documented deliverables (Lesson Plan, Handouts, Workbooks, PowerPoint Visuals).

  - 82:1 - ILT training, Complex subject matter, very custom, extended time spent on formatting classroom deliverables.

The ratios increase for basic eLearning. An average of 79 hours development time to 1 hour of actual training has been reported.

So, for a three hour class, a ballpark figure would be about a week of development.

I would like to caution you that providing basic, ad hoc training with no instructional design, lesson development, and other standard tasks often results in the need for retraining at a later date. If we have time to retrain, we have time to train right the first time.

Some other constraints are:

- How many Wi-Fi connections can the training rooms support? Each learner will need to work on her own laptop.

- What differences need to be addressed for distance learners?

- Trainees are also responsible for keeping current assignments on track.

- With remote trainees, scheduling may be difficult.

## The Project Statement of Purpose

The purpose for training is to have employees ready to use Artemis the day after training. They will know how to use each task, what comes before and after, and how to deal with differences in using Artemis when dealing with different journals/customers. Employees will also be able to perform tasks the rarely do (when covering for an absent employee, for example.) This training will also leave the learners confident in their use of Artemis.

# Front End Analysis

Typically, I’d do a front end analysis to get a big picture on what needs to be done. This includes full gap and performance improvement analyses. The following are more general than I’d like—time precluded doing a more in-depth analysis.

## Performance Improvement Analysis

### Gaps that can be closed through training

Process of using Artemis for each component.

### Gaps that cannot be closed through training:

None identified.

## Training Needs/Gap Analysis

### Desired performance

At the end of training, participants will be able to send a component through the Artemis system, from record creation to EPUB.

### Actual Performance

Unavailable.

### Performance gap = desired –measured

Unavailable

## Job Analysis

### Specific duty areas

TK

## Task analysis

See Task analysis on page 6.

## Learning Objectives

As this is a relatively flat/shallow product, the Primary Learning Objective is simply that the employee successfully moves a component through Artemis. Therefore, the Enabling Learning Objectives are similarly simple—the employee can complete each Artemis tasks successfully, building to completing a component’s movement through Artemis. We’re ignoring for now those tasks that aren’t part of his customer’s workflow, or a task that isn’t traditionally part of his job. For example, (IS) Vendor Invoices might not be part of his job. He’ll learn about it in the context of the Artemis flow.

# Target Audience

## Users

Our primary users are Production employees at DJS, seen as Production Editor below. Other users are shown in the graphic.

For this training, we’ll concentrate on Production Editors and Production Assistants. Since we’re familiar with this role, I don’t see the need to create a persona for them.

## Task Descriptions

Here are the Artemis tasks associated with each component. In addition to teaching each task, we will also provide an intro to Artemis, some background, and a wrap up. Please see Training Class Timelines on page 8:

And here are, the Artemis components and tasks. Note that components have similar tasks.

### Ads

| (AD) Record Created | (AD) Ad Processing | (AD) Ad QC |
| --- | --- | --- |
| (AD) eProof | (AD) Corrections | (AD) Corrections Review |
| (AD) Approval | (AD) Query |  |

### FMBM

| (FB) Record Created | (FB) Ticketless Graphics Processing | (FB) Ticketed Graphics Processing |
| --- | --- | --- |
| (FB) Traditional Composition | (FB) Composition QC | (FB) eProof |
| (FB) Manually Post Proof | (FB) Corrections | (FB) Corrections Review |
| (FB) Revised Proof | (FB) Revised Proof Review | (FB) Approval |
| (FB) Query |  |  |

### Article

| (AR) Record Created | (AR) Initial Files to Vendor | (AR) Artwork Services |
| --- | --- | --- |
| (AR) Graphics QC | (AR) Graphics Review | (AR) Image Forensics |
| (AR) Image Forensics QC | (AR) Image Forensics Corrections | (AR) Image Forensics Corrections Review |
| (AR) Graphics Processing | (AR) Graphics Processing (Ticketed) | (AR) LaTeX Conversion |
| (AR) Word Conversion | (AR) SI Processing | (AR) MS Prep |
| (AR) Tooling | (AR) FreeStyle Processing | (AR) FreeStyle QC |
| (AR) Files to Copy Editor | (AR) Copyediting | (AR) CE Invoice Received |
| (AR) Post CE Review | (AR) eGalley XML Export | (AR) Composition |
| (AR) Composition | (AR) Comp QC | (AR) Send Proof |
| (AR) eBill Estimate to Authors | (AR) Author Corrections | (AR) Editorial Office Corrections |
| (AR) Corrections Review | (AR) Proof Revisions | (AR) Proof Revisions QC |
| (AR) Press Interest Processing | (AR) PAP Processing | (AR) PAP QC |
| (AR) PAP Corrections | (AR) PAP Corrections Review | (AR) PAP Release |
| (AR) Permissions | (AR) Approval | (AR) Final Proof |
| (AR) eBill Invoice to Authors | (AR) Query | (AR) PE - Pre Comp QC |
| (AR) PE - Publisher Corrections |  |  |

### Issue

| (IS) Record Created | (IS) FTOC Processing | (IS) Cover Image Selection |
| --- | --- | --- |
| (IS) Report Generation | (IS) Customer-Supplied Lineup | (IS) Lineup |
| (IS) Lineup Corrections | (IS) Sequencing | (IS) Folio |
| (IS) Folio QC | (IS) Send Proof | (IS) Editorial Office Corrections |
| (IS) Corrections Review | (IS) Proof Revisions | (IS) Proof Revisions QC |
| (IS) Finalize Issue | (IS) Final Files | (IS) Final Files QC |
| (IS) Issue Release | (IS) EurekAlert | (IS) Files to Printer |
| (IS) Files Elsewhere? | (IS) Blues Corrections | (IS) Blues Corrections Review |
| (IS) Blues Revisions | (IS) Blues QC | (IS) Invoice to Authors |
| (IS) ELD Processing | (IS) ELD QC | (IS) ELD Editorial Office Corrections |
| (IS) ELD Corrections Review | (IS) ELD Approval | (IS) ELD Release |
| (IS) Vendor Invoice | (IS) Customer Invoice | (IS) Copyright Forms to Editorial Office |
| (IS) Files Archived | (IS) Query | (IS) ePub |

Now, I know it looks intimidating. But remember that Artemis, at the basic level, merely pushes things—an ad, article, front or back matter, issue—from one status to another. And often what happens is automatic. For example, in (AR) Initial Files to Vendor, the employee loads the files and directs Artemis to send them. When the Vendor returns the files, Artemis notifies the employee that the Vendor has returned the files and then she can continue working on them. Now, I’m NOT minimizing the work. What I am saying is that this makes the training easier. All we need to answer are three, basic questions:

- What is the task?

- How do I do it?

- What happens if I make a mistake?

What we also have to do in the training is relate the tasks in such a way as to make it all ‘make sense’ to the learner.

# Training Class Timelines

It is difficult to estimate the time needed to train, but a SWAG, ballpark figure is as follows:

- Intro– 45 mins/1 hour of day.

  - What this course will do

    - How it is structured

    - What methods we’ll use (assign each learner their own assets to use during the class)

    - Housekeeping (breaks, questions, etc.)

  - Introduce Artemis

    - How does Artemis fit in with our strategy?

    - How is Artemis different from the current system?

    - ArticleExpress overview

- Component Tasks as listed in Task Descriptions, page 6.

  - Walk through each task.

  - Differences for each customer (workflow) raised in the discussion and addressed. However, we won’t teach each individual workflow.

- Wrap up 15 mins-30 mins.

  - What you learned and what you can do NOW with Artemis.

  - Where to go for more assistance (Online Help, videos, job aids)

  - Other training available.

  - Feedback forms.

In addition to the above, for each training class, here’s a general schedule

| Time | Preparation tasks |
| --- | --- |
| 2 weeks before the session | Identify and create a list of participants. Send a session introduction and welcome letter to all participants and describe any pre-work required. |
| 3 work days before the session | Send an e-mail message to all participants to remind them of the upcoming session and to confirm they have downloaded the session materials. If applicable, describe any preparation required. Review the facilitator guide, participant guide, and session slides to ensure you are familiar with the content. For participants that registered or were added late for the session, send an introduction and welcome letter and describe any pre-work required. |
| The morning of the session | Be ready at least one hour ahead of time to make certain there are no technical concerns. Test projectors, microphones, Wi-Fi, etc. |
| 1 work day after the session | E-mail a feedback survey to participants. We can use Articulate or Google Docs to do it for nothing. Remind participants where they can find resources to help. |
| 2 work days after the session | Provide assessment feedback from participants’ post-tests if you’ve given them any. |
| 2 weeks after the session | Follow up with participants on survey results or email about the session. |

We’ll actively solicit feedback – signed or unsigned – to help improve the training.

# Usability Goals (Requirements)

What are our usability goals and how can we tell if the training is successful? We’ll know that if employees start using Artemis and there isn’t an excessive number of questions into Technology. We’ll need to track and address these by improving the Help and/or training.

We’ll also use a survey at least a day after the training to gauge its effectiveness.

# Existing Documentation

The online Help will be available before the training, and accessible during training. We hope we can leverage each – training and online Help – to create great documentation and training.

# Product Design Implications

The Artemis interface is a simple, form-driven design. It is certainly easier than the existing FileMaker interface. Instead of showing everything at once, the user can go through the interface in a methodical and logical flow. As such, it lends itself to easy teaching.

# Document Specifications

We’ll supply the training as PowerPoint presentations and associated documents.

## Instructional Design

I considered using ADDIE (Analysis, Design, Develop, Implement, Evaluate) as our ID model, but the timeframe and resources make it unrealistic. Instead, we are using SAM (Successive Approximation Model) for the Artemis training. This is a rapid, iterative concurrent design/development approach. It is well-suited to project with short timeframes and training small groups. We can produce prototype lessons, see if they make sense, and go from there. Here’s a graphic that might help:

I think it is a good choice for our situation.

## Platforms Supported

As Artemis is a web-based application, we don’t have any platform concerns.

## Graphics and Media

Most of the graphics and media will be live. That is, we will be showing Artemis in action. Any screen shots or recordings, as well as swim-lane diagrams will be created for the training. We don’t anticipate any ‘gotchas’ here.

## Delivery

Delivery is live, stand up classroom training and GoToMeeting sessions. We may record training sessions for later use. In addition, we may also ‘boil down’ classroom training into Articulate videos.

## Extras

While we’ll provide the learners with training materials such as hard copies of the PowerPoint and other training documents, we may also provide a printer Quick Reference or other job aids. The extras will depend primarily on what the users say they want or what’s determined to be useful for completing tasks.

# Process, Estimates, and Schedule

## Milestones

We’ve identified the following milestones:

- Front End Analysis

- Instructional design

- Lesson development

- Facilitator/participant guide development

- Stakeholder reviews

I am estimating 115 topics for the training. Some of these overlap, are similar to each other, or are exactly the same, such as (AD) Record Created, (FB) Record Created, (AR) Record Created, and (IS) Record Created. I’ve taken this into account in my calculation. We’ve done a lot of the front end analysis and instructional design. I am not prepared to give firm dates at this time—however, here is an estimate based on what I know so far:

|  | Number | Weighting factor | Totals |
| --- | --- | --- | --- |
| Size of Document: |  |  |  |
| # of topics | 115 | 0.15 | 17.3 |
| Subtotal: |  |  | 17.3 |
| Type of Document |  |  |  |
| New: create content, edit, format |  | 1 | 17.25 |
| Update: add NEW content, edit & format |  | 0.75 | 12.94 |
| Complexity of Content |  |  |  |
| Low |  | 0 | 0.00 |
| Medium |  | 0.5 | 8.63 |
| Document Source |  |  |  |
| Microsoft Word |  | 0.75 | 12.94 |
| Other |  | 1.25 | 21.56 |
| Formatting |  |  |  |
| Use existing template? |  | 0.25 | 4.31 |
| Graphics (includes only new or updated graphics) |  |  |  |
| More than 10 |  | 1 | 17.25 |
| Deliverables |  |  |  |
| print/pdf |  | .75 | 12.94 |
| online (HTML, CBT) |  | .75 | 12.94 |
| Word doc |  | 0.5 | 8.63 |
| Review Cycle |  |  |  |
| # of reviewers, stakeholders | 6 | 0.25 | 1.50 |
| full (proof, content, structure) reviews required? |  | 0.50 | 8.63 |
| Project Totals: |  |  |  |
| # project hours required |  |  | 139.50 |
| # of person days |  |  | 17.44 |
| # of person weeks |  |  | 3.42 |

As we get more data, we can refine the schedule and add actual dates to the milestones.

## Reviews and Approvals.

Stakeholders and other reviewers must review for technical accuracy, structure, and copy. Reviews will be in parts as we develop, and as a whole at the end. This assures correcting information before it is too late as well as having the entire training reviewed as a whole.

# Resources

## Documentation Team

Steve Arrants will be writing the Online Help and Artemis training.

Susan Clark will be assisting in the design and creation of the training as well as delivering it.

## Other Teams

Steve Haenel and Beth Foy will be our technical/SME contacts.

TK

## Hardware, Software, Tools

We’ll be using a mix of Word, PowerPoint, Articulate, Camtasia, and other tools to develop and deliver training.

## Assets

We will need to create an asset bank for training. Each learner needs to have his own set of files—we don’t want folks using the same files at the same time! We’d like to wipe the Artemis database used for training after each class so that we don’t have to continually recreate assets and can reuse what we have.

Susan Clark has identified these customer/journal pairs for our assets:

| Customer | Journal |
| --- | --- |
| ATS | RCCM |
| ASPET | JPET |
| PNAS | PNAS |
| AMS | JCLI |
| AAI | JI |
| Cell Press | Cell |
| ASNutr | AJCN |
| ADA | DB |
| ASH | Blood |
| ASPP | PP |

# Potential Risks and Issues

Any project can go south quickly. We need to start and work rapidly. Reviewers, stakeholders—anyone involved—must surface issues as they occur. The only potential issue I can see is if we need to switch gears and create/provide training to customers before we’ve completed employee training and assessed feedback.

Chapman Alliance “How Long Does it take to Create Learning” webinar.